## Sheet1
Bug_ID | Date | Status | Module | Test data | Detail | Bug Type | Reported By | Fixed By | Resolution/Remark | QA Remarks
1 | 27thJuly23 | Open | Chekin/Out | CheckIn- and Checkout click | If we CheckIn and CheckOut Few times then its taking too long for next action mean Loading........few min 2 to 3 min. | Functional | Raja | Ajay | done
2 | 27thJuly23 | Open | Chat | Chat | If you chat more than one group, and switch between groups then it shows screen blinking(Loading....) Taking long time. Even if we move to other tabs like Dashboard it shows loading... | Functional | Raja | Ajay | fixed | Still Loading.
3 | 27thJuly23 | Open | Chat | Chat | Show the chat history from last seven days only.. Currently it shows from the bigining | Performance | Raja
4 | 27thJuly23 | Open | QR Code Generation | 44 | QR Code generated from Admin website not working. If we generate from online it works fine. | Functional | Raja
5 | 27thJuly23 | Open | Tracking Data | Moved around | There not tracking details logged. Tracking not found | Functional | Raja | Ajay | done
6 | 27thJuly23 | Open | Chat | Chat | Last message not shows untill scroll down or Keyboard. | Functional | Raja
7 | 27thJuly23 | Open | Chat | Chat | Chat notification count shows but not shows on group. | Functional | Raja
8 | 28thJuly23 | Open | Clock In/ Clock Out | Click | It taking time on every action, Loader shows for 2 to 4 min. | Performance | Raja
9 |  | Open | Dashboard | header | Event details not shows correctly. it W&S Open / WS Tennis 22 on other device. | Functional | Raja | Ajay | done
10 |  | Open | Chat | Send msg | Chat Notification count not shows on Dashboard screen | Functional | Raja. | Ajay | done
11 | 31st July | Open | Generate Rotation | Six Combined positions | Click on generate rotation, Nothing shows. | Functional | Raja | Nirbhay | done
12 | 31st July | Open | Schedule | Jeffrey Bruewer | Search result not visible if user scrolls down before searching, it shows blank page on search, Mean scroll not reset. Once you scroll up after search it shows | Functional | Raja | Vivek C |  | Its due to Scroll issue, Before search if user scroll down the page in users list then the scroll not resets, then if you search any it not shows.
13 | 31st July | Open | Dashboard/Chat | Notification count | When we click on Notification count, the chat pop up opens but not shows the message for count. It says no history for the day... | Functional | Raja
14 | 31st July | Open | Mobile app/ My Tournament Schedule | Month and date | If the my current schedule shows next month, The heading shows current month and year, the below it shows next month schedule dates its confusing. Example: Today date is 31st July and my tournment schedule is For August 13th to 25th then it shows JUL23 below MON 13th, TUS14th,...SAT25th. | GUI | Raja | Refer the below image. |  | Discussed with Nirbhay
15 | 31st July | Open | Rotation | New Organization | Rotation Not creating. | Functional | Raja | Nirbhay | Done. Need to test
16 |  | Open
17 | 1st Aug | Open | Sub Menu Icon | Click | Give the click on Sub Menu Icon. | GUI | Raja. | Vivek C
18 | 1st Aug | Open | Users | Click multiple times on Save | It will create duplicate users. Disable the save button once it clicked | GUI | Raja. | Vivek C
19 | 1st Aug | Open | QR Generation | Edit and enter any number | It creates new QA Code. | Functional | Raja.
20 | 1st Aug | Open | Role Profile | Scroll down | Freeze the header, when we scroll down, the header not shows, its confusing which is add, edit and delete. | GUI | Raja. | Vivek C
21 | 1st Aug | Open | URL Change | Copy paste the url after login low user rights, #/feature/settings/role-profiles | We can access all pages by changing url. | Functional | Raja. | Vivek C
22 | 1st Aug | Open | Role Profile | Rotation Review | This role not shows when user logged in with Rotation Review Profile. | Functional | Raja. | Nirbhy | Done
23 | 1st Aug | Open | Settings/ Positions/ Position Priority | Position not entered, Mean it blank | If user checks in it considered as critical postion. | Functional | Raja. | Nirbhy | Done
24 | 2nd AUG | Open | Dashboard / BELL Icon | Notification , Submit late request from app | Submit the late request from app but not shows under notifications BELL icon | Functional | Raja.
25 | 2nd AUG | Open | App/Chat | Message count | Msg count shows but it shows even after reading, until reply. | Functional | Raja.
26 | 2nd AUG | Open | Dashboard / Chat Count | Message count | Chat message count shows In Negative after reading. | GUI | Raja. | Vivek P
27 | 3rd AUG | Open | Web Dashboard/Shift Log | Image upload | Image Upload not working from shiftlog | Functional | Raja | Vivek C
28 | 3rd AUG | Open | Reports/ Shift log | Eneter more than 10 messages | Not shows more than 10 messages, and latest should shown on top | Functional | Raja | Vivek C
29 | 3rd AUG | Open | Reports/ Shift log | Click on Save multiple times or wihtout msg, | It show Null in log. | Functional | Raja. | Vivek C
30 | 3rd AUG | Open | Today's Schedule | Change SID | On assigning SID, Change SID and Unassign, Not working properly. | Functional | Raja
31 | 3rd AUG | Open | Today's Schedule /Site view | Click on Locate | Not shows user location, just it loads the map. | Functional | Raja | Vivek C |  | Verified.
32 | 3rd AUG | Open | Mobile | From Dashboard to Chat | Shows somthing went wrong. On Ok shows loader. | Functional | Raja
33 | 3rd AUG | Open | App/Chat | Send Message Chat | Send chat msg after 1hr, the msg will not delivered until you restart the app | Functional | Raja
34 | 8th Aug | Open | Web/Dashboard | Shift Log | Critical Position Not Staffed --> Positions Not Staffed | GUI | Raja
35 | 8th Aug | Open | Shift Log | Copy paste the text and Upload a picture/doc | Print Doc PDF Shows tags and image not shows | Functional | Raja
36 | 8th Aug | Open | Today's Schedule | Click on edit menu | Change SID if user selects SID from List then the Auto option should be unchecked. | Functional | Raja.
37 | 8th Aug | Open | Assign Fixed Role | Add new role, WatchAudiance | Add new role not works, after adding not shows in the list | Functional | Raja
38 | 8th Aug | Open | Mobile app | Shedule , Scan QR Code | Able to scan QR for 2hr later shift | Functional | Raja | Fixed/ |  | Verified.
39 | 8th Aug | Open | web/Event / Bulletins | Edit Bulletin | Add bulletin without Publish date, on Edit it shows Nan In all fields | Functional | Raja
40 | 10th Aug | Open | Reports/ Shift log | Click on reports/ Import XLS | The Import xls shows wrong heading for all reports except Marshal Work Hours Report | Functional | Raja
41 | 10th Aug | Open | Supervisor | Click on View on any record | Click on view then change the date close the view popup, then view any other record then it shows the previous record date. Should reset to current date. | Non Functional | Raja
42
43 |  |  | Tracking Data |  | In Tracking speed shows -1 (What is it mean) and there is no units
|  |  |  | Users | XLS
|  |  |  | Bob Detrick(C) | Bob Detrick
|  |  |  | Edward M. Barloh(C) | Edward M. Barloh
|  |  |  | Jorge Abadia | Jorge Cuautle Abadia
|  |  |  | Rob Illig - Marshal Scheduler(C) | Rob Illig - Marshal Scheduler
|  |  |  | NOt Found | Mark Parsons
|  |  |  | Mark Prince - Marshal Scheduler(C) | Mark Prince - Marshal Scheduler
|  |  |  | NOt Found | Robin Sauer
|  |  |  | Barbara Sferra(C) | Barbara Sferra
|  |  |  | Gary E Varga-Toth | Gary E Toth